## Task List
Task | Time | Dependencies? | Note
Adapt Codebase
Create Card Database | 2 | system design
Determine win/loss/end
Design Card system | 1 |  | In-class
Design Map

## Work Assigned
Each member of the team will commit 2-3 hours out of class to this project
Each chunk can support 1 or 2 hours or work
| Week 10 | 2026-03-20 | Week 11 | 2026-03-27 | Week 12 | 2026-04-03 | Week 13 | 2026-04-10 | Week 14 | 2026-04-17
| ChunkA | ChunkB | ChunkA | ChunkB | ChunkA | ChunkB | ChunkA | ChunkB | ChunkA | ChunkB
Dr. L-A | Codebase fixing
Lillian | Codebase fixing
Peter | Map & Movement
Jourdan | Map & Movement
Khaliq | Map & Movement
Dan | Card Database
Joe | Card Database
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Weeks run on class date (Fri.)
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Weeks run on class date (Fri.)
Note on G4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Weeks run on class date (Fri.)
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Weeks run on class date (Fri.)
Note on K4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Weeks run on class date (Fri.)
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Weeks run on class date (Fri.)